## Sheet1
Id | requirment name | Description | MOSCO | complexity | status | tested | testing date
1 | project startup/ Anlysis and Requirements
1.1 | search memory game topic | search journal and other resources about the memory game |  | easy | done
1.2 | search demenia topic | search journal and other resources about the disease and link the two topics |  | easy | done
1.3 | preliminaries work | Search about preliminaries work and how the project is an improvement |  | meduim | done
1.4 | finalize project features | based on the research done, decide the features of the app |  | meduim | done
1.5 | gather requirments | idenfty the requirements of the project |  | meduim | done
1.6 | Validate the requirements | Confirms that a requirement meet the operational and system-level needs of the program |  | easy | done
1.7 | verifying the requirements | Confirms that the requirements can meet the intended objective of what it is meant for. |  | easy
2 | desiging stage
2.1 | App type | decide what sort of app to do and what language to use to implement it |  | easy | done
2.2 | life cycle | decide on a project life cycle |  | easy | done
2.3 | requirements | review the requirements to to design the app based on it |  | meduim | done
2.4 | Game framework | simple framework for the game |  | easy | done
2.5 | Design database | created Entity Relation Modal and logical data model |  | easy | done
2.6 | ERD and LDM | decide the necessary attributes that would go in the entities. |  | easy | done
2.7 | prototype | Implement an intial working solution for the game |  | meduim | done
3 | implementation stage
3.1 | Initialise a database | get a database running with the client side | Must have | easy | done | passed | 2022-09-29
3.2 | backend/frontend connection | connect the database with the client side | Must have | easy | done | passed | 2022-09-29
3.3 | create the tables | create tables for the users and images with suitable attributes to store the data in | Must have | easy | done | passed | 2022-09-29
3.4 | create a mock user | setup mock users in the database | Must have | easy | done | passed | 2022-10-03
3.5 | create UI | create a simple user interface for the welcome/landing page | Must have | meduim | done | passed | 2023-02-16
3.6 | create UI | create a register page | Must have | easy | done | passed | 2022-10-03
3.7 | login | create a user using the register page and insert their data to database | Must have | meduim | done | passed | 2023-03-05
3.8 | signin | sign in an exsiting user | Must have | easy | done | passed | 2023-03-01
3.9 | import files | enable the user to uplaod files | Must have | high | done | passed
3.1 | descripe the photo | enable the user to write a little text about each photo | Should have | meduim | done | passed
3.11 | store the files | store the files for each user seperately in the database | Must have | meduim | done | passed
3.12 | display image | display all the uploaded images on the screen | Could have | meduim | done | passed | 2023-03-10 | images won't be displayed in a table | used php code to display/ try diffrerent approach
3.13 | delete images | enable the user to delete photos if they want to | Should have | meduim |  | failed | 2023-03-10 | when clicking a delete button it failed to run the related function
3.14 | UI to start the game | create an instructions or tour to show the user how play and tackle the game | Should have | meduim | done
3.15 | fetch the files | pull the photos from the database to be used for the game | Should have | high | done | passed
3.16 | UI for the game | create a n*n grid with photos | Must have | meduim | done | passed
3.17 | Game logjc | Set all photos facing down first | Must have | meduim | done | passed
3.18 | Game logjc | The user can reveal only 2 photos at a time by clicking on them | Must have | high | done | passed
3.19 | Game logjc | set photo face down again if match is not found | Must have | hard | done | passed
3.2 | Game logjc | Set photos face up when a match is found | Must have | hard | done | passed
3.21 | Game logjc | set the match photos to un-clickable | Must have | meduim | done | passed
3.22 | produce a feedback | produce a simple feedback for the user | Could have | meduim | done | passed
3.23 | Game logjc | When all pairs are found, produce a congrats message and restart the game | Should have | meduim | done | passed | 2023-03-09
3.24 | Game logjc | randomize the array of photos to play the game again | Must have | easy | done | passed
3.25 | Defficulty level | enable the user to choose from easy to hard level | Could have | easy | done | passed | 2023-03-07
3.26 | Defficulty level | randomly the right number of photos upon chosen a level of difficulty | Could have | meduim | done | passed | 2023-03-07
3.27 | Motivation messages | Encouraging messages as the user play | Could have | meduim
3.28 | accessbilty | consider some accessbilty criteria such as the font used and the design of the application | would have | meduim | done | passed
3.29 | responsive design | making the application responsive to different devices | Should have | hard | maybe? | passed
3.3 | make it pretty | make the game look nice | Should have | hard | done | passed
3.31 | sound effect | produce a sound effect to the game when playing. | Could have | meduim | done | passed | 2023-03-09
3.32 | add the discription | display the discription with photo during the game | Could have | hard
3.33 | Timer | Set a timer for the game | Won't have | meduim | N/A
3.34 | Auto-complete | Give the user the option for auto complete. | Won't have | high | N/A
3.35 | Shuffle | Shuffle the locations of the photos | Won't have | high | N/A
3.36 | user experince | make user experience nice
4 | testing stage
4.1 | get in touch with users | get in touch with potentional users to get them to test the software
4.2 | meet the users | arrange a meeting with the users to explain about the game
4.3 | get the users to test | give the users the access to the game
4.4 | gathering feedback | arrange another meeting with each user to get a feedback
4.5 | improvement | based on the feedback improve the game if possible
5 | Evaluating
5.1 | review the requirements | evalute how much of the requirements were met
5.2 | future work/improvement | create a list of future work or any improvements maybe done
5.3 | lessons learned
5.4 | conclusion